## RYDA Master Tracker
RYDA ¦ COMPREHENSIVE OPERATIONAL TRACKER
| Not Started | In Progress | Complete | N/A |  | PRIORITY: | High | Medium | Low
# | Workstream | Task | Priority | Owner | Status | Target Date | Completion Date | Blocked By | Notes | Market | Link / Doc
COMPANY FORMATION
1 | Company Formation | Choose and register company name (RYDA LLC or chosen entity) | High | CEO/CTO | Not Started |  |  |  |  | All
2 | Company Formation | Form Delaware LLC — articles of organization filed and accepted | High | Legal | Not Started |  |  |  |  | All
3 | Company Formation | Obtain EIN (Employer Identification Number) from IRS | High | CFO/COO | Not Started |  |  |  |  | All
4 | Company Formation | Open business bank accounts — operating account + reserve account | High | CFO/COO | Not Started |  |  |  |  | All
5 | Company Formation | Open company credit card for operational expenses | Medium | CFO/COO | Not Started |  |  |  |  | All
6 | Company Formation | File any required DBA (doing business as) registrations | Medium | Legal | Not Started |  |  |  |  | All
7 | Company Formation | Draft and execute founder agreements and RYDA LLC operating agreement | High | Legal | Not Started |  |  |  | Covers equity split, roles, vesting, IP assignment | All
8 | Company Formation | Obtain required business licenses for first launch state (FL) | High | Legal | Not Started |  |  |  | Check FL Dept of Business & Professional Regulation | All
9 | Company Formation | Register as qualified foreign LLC in CA and NY before those market launches | High | Legal | N/A |  | 2026-05-07 |  | Required before operating in each state ¦ Future: FL only at Q3 2026 launch. CA + NY foreign-LLC registration scoped for 2027 expansion | All
10 | Company Formation | Establish organizational chart — current structure and reporting lines | Medium | CEO/CTO | Not Started |  |  |  |  | All
11 | Company Formation | Identify and retain legal counsel — fractional ownership and securities experience required | High | CEO/CTO | Not Started |  |  |  | Critical early hire; interim counsel acceptable initially | All
12 | Company Formation | Identify and retain CPA / tax advisor with LLC pass-through experience | High | CFO/COO | Not Started |  |  |  |  | All
13 | Company Formation | Recruit at least 1 advisor with luxury automotive or marketplace experience | Medium | CEO/CTO | Not Started |  |  |  |  | All
14 | Company Formation | Set up registered agent service in all operating states | Medium | Legal | Not Started |  |  |  |  | All
15 | Company Formation | Set up accounting software (QuickBooks, Xero, or equivalent) | High | CFO/COO | Not Started |  |  |  |  | All
16 | Company Formation | Establish chart of accounts appropriate for RYDA's multi-revenue model | High | CFO/COO | Not Started |  |  |  | Rental commission, mgmt fees, membership, transfers | All
LEGAL & CONTRACTS
17 | Legal & Contracts | SEC / securities counsel review — confirm co-ownership LLC structure does not require registration | High | Legal | Not Started |  |  |  | Critical — must be done before first co-owner is solicited | All
18 | Legal & Contracts | Rental marketplace listing agreement — contract with rental operator partners | High | Legal | Not Started |  |  |  | Governs commission, liability, brand use, termination | All
19 | Legal & Contracts | Rental booking terms and member waiver (liability, damage, conduct) | High | Legal | In Progress |  |  |  | Member-facing document on platform ¦ Partial: drafts in /legal/terms + sample-documents UI. Final lawyer review pending | All
20 | Legal & Contracts | Co-Owner Agreement — core document governing member rights, usage, costs, exit | High | Legal | In Progress |  |  |  | Most important legal document in co-ownership track ¦ Partial: LLC amendment PDF template at src/lib/llc-amendment-pdf.tsx; sample doc surface at /sample-documents. Full Co-Owner Agreement awaiting securities counsel | All
21 | Legal & Contracts | Vehicle LLC operating agreement template — single-purpose LLC per co-owned vehicle | High | Legal | In Progress |  |  |  | One LLC per vehicle; all co-owners sign ¦ Partial: src/lib/llc-amendment-pdf.tsx generates per-vehicle amendment; full OA template awaiting legal | All
22 | Legal & Contracts | Share transfer and exit protocol document | High | Legal | In Progress |  |  |  | Defines process, valuation method, transfer fee ¦ Partial: process documented at /how-it-works#exit + /faq (90-day hold, 75% supermajority, member-to-member transfer). Formal legal template pending counsel | All
23 | Legal & Contracts | Independent owner agreement — for private owners selling partial interest to a group | High | Legal | Not Started |  |  |  | Covers retained share, usage rights, obligations | All
24 | Legal & Contracts | Referral partner agreement — real estate agents, wealth advisors, concierge | Medium | Legal | Not Started |  |  |  | Referral fee, payment terms, exclusivity (if any) | All
25 | Legal & Contracts | Privacy policy and terms of service for ryda.com | High | Legal + CEO/CTO | In Progress |  |  |  | Required before launch; covers data, liability, disputes ¦ Partial: drafts shipped at /legal/privacy, /legal/terms, /legal/cookies, /legal/accessibility, /legal/disclaimer. Audit flagged: needs named-processor list + GDPR section | All
26 | Legal & Contracts | NDA / confidentiality agreement template for partners, advisors, contractors | Medium | Legal | Not Started |  |  |  |  | All
27 | Legal & Contracts | Intellectual property assignment agreements for all founders and contractors | High | Legal | Not Started |  |  |  | All IP created must vest in RYDA LLC | All
28 | Legal & Contracts | Non-solicitation and non-compete agreements for founders and key contractors | Medium | Legal | Not Started |  |  |  | Adapted for FL, CA, NY enforceability | All
29 | Legal & Contracts | Storage facility partnership agreements — one per market | High | CFO/COO + Legal | Not Started |  |  |  | Revenue share or flat rate; access rights; liability | All
30 | Legal & Contracts | CPO dealer relationship agreements — preferred buyer terms | Medium | CFO/COO + Legal | Not Started |  |  |  | Not always a formal agreement but document key terms | All
31 | Legal & Contracts | Detailing and vehicle servicing partner agreements | Medium | CFO/COO | Not Started |  |  |  | SLA, pricing, turnaround, access to storage facility | All
32 | Legal & Contracts | Roadside assistance coverage agreement for co-ownership vehicles | High | CFO/COO | Not Started |  |  |  |  | All
33 | Legal & Contracts | Platform development agreement with technology vendor | High | CEO/CTO + Legal | N/A |  | 2026-05-07 |  | IP ownership, deliverables, warranties, SLAs ¦ Built in-house — no external platform vendor; IP vests in RYDA LLC by default | All
34 | Legal & Contracts | Review and maintain list of all active contracts — update at least quarterly | Medium | CFO/COO | Not Started |  |  |  | Including all partner, vendor, and member contracts | All
35 | Legal & Contracts | Establish process for contract renewals and expiration tracking | Medium | CFO/COO | Not Started |  |  |  |  | All
FINANCE & ACCOUNTING
36 | Finance & Accounting | Build 3-year financial model — revenue, OPEX, EBITDA by market and track | High | CFO/COO | Not Started |  |  |  | Model rental commission + mgmt fees + membership separately | All
37 | Finance & Accounting | Establish monthly P&L reporting cadence — by market and by revenue stream | High | CFO/COO | Not Started |  |  |  |  | All
38 | Finance & Accounting | Set up accounts receivable process — rental commissions, management fees, membership | High | CFO/COO | Not Started |  |  |  |  | All
39 | Finance & Accounting | Set up accounts payable process — storage, detailing, platform, legal, insurance | High | CFO/COO | Not Started |  |  |  |  | All
40 | Finance & Accounting | Establish monthly bank reconciliation process | High | CFO/COO | Not Started |  |  |  |  | All
41 | Finance & Accounting | Establish cash flow forecasting — monthly, 13-week rolling | High | CFO/COO | Not Started |  |  |  | Critical for a capital-light business with lumpy revenue | All
42 | Finance & Accounting | Set up vehicle LLC bank accounts — one per co-owned vehicle | High | CFO/COO | Not Started |  |  |  | Used to collect co-owner funds and pay vehicle costs | All
43 | Finance & Accounting | Implement expense policy — approval thresholds, reimbursement, receipts | Medium | CFO/COO | Not Started |  |  |  |  | All
44 | Finance & Accounting | Set up payroll system if/when employees are hired (Gusto, ADP, Rippling) | Medium | CFO/COO | N/A |  | 2026-05-07 |  | Start with contractors; switch to payroll as team grows ¦ Future: payroll setup deferred until first W-2 hire | All
45 | Finance & Accounting | Establish commission tracking — rental partner payouts vs. RYDA retention | High | CFO/COO + CEO/CTO | In Progress |  |  |  | Automated via platform where possible ¦ Partial: Stripe webhooks track all payments; share_purchases + bookings tables in Supabase; reporting layer pending | All
46 | Finance & Accounting | Establish management fee invoicing and collection process for vehicle LLCs | High | CFO/COO | Not Started |  |  |  | Quarterly billing recommended | All
47 | Finance & Accounting | Set up annual budget process — plan vs. actual tracking by month | Medium | CFO/COO | Not Started |  |  |  |  | All
48 | Finance & Accounting | Vehicle depreciation schedule — track value of any RYDA-owned assets | Medium | CFO/COO | Not Started |  |  |  | Relevant if RYDA ever holds fleet assets directly | All
49 | Finance & Accounting | Cap table management — track RYDA LLC membership interests, any future investors | High | CFO/COO + Legal | Not Started |  |  |  | Use Carta or equivalent | All
50 | Finance & Accounting | Investor reporting template — monthly or quarterly for seed investors | Medium | CEO/CTO + CFO/COO | Not Started |  |  |  | Revenue, KPIs, burn rate, milestones | All
TAX & COMPLIANCE
51 | Tax & Compliance | Establish federal tax filing calendar — LLC pass-through returns (Form 1065) | High | CFO/COO + CPA | Not Started |  |  |  |  | All
52 | Tax & Compliance | Determine state income / franchise tax obligations in FL, CA, NY | High | CFO/COO + CPA | Not Started |  |  |  | CA franchise tax applies even to LLCs | All
53 | Tax & Compliance | Determine sales tax obligations — rental transactions in each state | High | CFO/COO + CPA | Not Started |  |  |  | FL, CA, NY all have complex rental tax rules | All
54 | Tax & Compliance | Register for sales tax collection and remittance in FL before first rental booking | High | CFO/COO + CPA | Not Started |  |  |  | FL imposes sales tax on rental of tangible personal property | All
55 | Tax & Compliance | Determine if short-term vehicle rental triggers additional licensing in FL, CA, NY | High | Legal | Not Started |  |  |  | Some states treat rental operators as dealers — verify | All
56 | Tax & Compliance | Set up sales tax collection in platform payment system — automated where possible | High | CEO/CTO + CFO/COO | Not Started |  |  |  |  | All
57 | Tax & Compliance | Issue 1099s to all contractors and referral partners paid $600+ annually | High | CFO/COO | Not Started |  |  |  | Annual requirement — track carefully from day one | All
58 | Tax & Compliance | File Form 940 and 941 when employees are hired | High | CFO/COO + CPA | N/A |  | 2026-05-07 |  | Payroll tax; not applicable until first W-2 employee ¦ Future: Form 940/941 not applicable until first W-2 employee | All
59 | Tax & Compliance | Establish escheat / unclaimed property compliance process | Low | CFO/COO + CPA | Not Started |  |  |  | Applies to unclaimed member deposits or balances | All
60 | Tax & Compliance | Annual state registration renewals — all operating states | High | CFO/COO + Legal | Not Started |  |  |  | FL, CA, NY all require annual renewal filings and fees | All
61 | Tax & Compliance | File annual reports for all active LLCs — RYDA LLC and each vehicle LLC | High | CFO/COO + Legal | Not Started |  |  |  | Penalties for late filing can be significant | All
62 | Tax & Compliance | Maintain records of all co-owner capital contributions and distributions per vehicle LLC | High | CFO/COO | Not Started |  |  |  | Required for accurate K-1 issuance | All
63 | Tax & Compliance | Issue Schedule K-1s to all co-owners annually for each vehicle LLC | High | CFO/COO + CPA | Not Started |  |  |  | Pass-through tax reporting obligation | All
64 | Tax & Compliance | Determine if RYDA's management fee income is subject to self-employment tax | Medium | CFO/COO + CPA | Not Started |  |  |  |  | All
65 | Tax & Compliance | Maintain transfer pricing documentation for intercompany charges between LLCs | Medium | CFO/COO + CPA | Not Started |  |  |  | Relevant as vehicle LLC count grows | All
INSURANCE
66 | Insurance | Identify and engage specialty exotic / commercial fleet insurance broker | High | CFO/COO | Not Started |  |  |  | Hagerty, American Collectors, or specialty fleet broker | All
67 | Insurance | Obtain commercial fleet insurance policy — agreed-value coverage on all co-owned vehicles | High | CFO/COO | Not Started |  |  |  | Confirmed in writing before any vehicle purchase | All
68 | Insurance | Confirm rental partner vehicles are insured by partner — get certificates of insurance | High | CFO/COO | Not Started |  |  |  | RYDA must not have exposure on rental partner vehicles | All
69 | Insurance | Bind general liability insurance for RYDA LLC operations | High | CFO/COO | Not Started |  |  |  | Covers platform operations, events, non-vehicle liability | All
70 | Insurance | Obtain Directors & Officers (D&O) liability insurance once board/investors are in place | Medium | CFO/COO | N/A |  | 2026-05-07 |  | Required for most institutional investors ¦ Future: D&O typically required by institutional investors; not yet | All
71 | Insurance | Obtain Errors & Omissions (E&O) / professional liability insurance | Medium | CFO/COO | Not Started |  |  |  | Covers liability from platform errors or advice given to members | All
72 | Insurance | Obtain cyber liability insurance — covers data breach, platform failures | High | CFO/COO | Not Started |  |  |  | Required given member PII and payment data handled | All
73 | Insurance | Confirm all co-owners are listed as named insureds on vehicle LLC fleet policy | High | CFO/COO | Not Started |  |  |  | Must be done for every new co-owner added | All
74 | Insurance | Establish annual insurance renewal calendar — all policies | Medium | CFO/COO | Not Started |  |  |  |  | All
75 | Insurance | Maintain schedule of all active insurance policies — insurer, coverage, premium, renewal | Medium | CFO/COO | Not Started |  |  |  |  | All
76 | Insurance | Establish claims process and 24-hour emergency contact protocol | High | CFO/COO | Not Started |  |  |  | Document and share with all members and staff | All
77 | Insurance | Review insurance requirements annually as fleet and member count grows | Medium | CFO/COO | Not Started |  |  |  |  | All
78 | Insurance | Obtain umbrella / excess liability policy above primary fleet and GL coverage | Medium | CFO/COO | Not Started |  |  |  | Recommended given high-value vehicle exposure | All
TECHNOLOGY & PLATFORM
79 | Technology & Platform | Acquire domain (ryda.com or chosen domain) and set up DNS | High | CEO/CTO | Complete |  | 2026-05-07 |  | ryda.pro registered (Namecheap) + Cloudflare DNS + Vercel deploy + Email Routing. See docs/dns-records-namecheap.md | All
80 | Technology & Platform | Finalize brand identity — logo, color system, typography, brand guidelines | High | CEO/CTO | Complete |  | 2026-05-07 |  | Wordmark logo at /profile-image (1080x1080 PNG). Fraunces serif + Inter sans. Brand red #DC4747. Full token system in src/app/globals.css. Social profile pic at ~/Desktop/ryda-profile-1080.png | All
81 | Technology & Platform | Select and contract platform development partner | High | CEO/CTO + Legal | N/A |  | 2026-05-07 |  | IP ownership clause required in contract ¦ Built in-house with AI-assisted dev; no external vendor agreement needed | All
82 | Technology & Platform | Define MVP platform scope: rental listings, booking, member signup, co-ownership marketplace | High | CEO/CTO | Complete |  | 2026-05-07 |  | MVP scope shipped: rental listings + booking + co-ownership marketplace + member signup + KYC + admin tools. See src/app/ | All
83 | Technology & Platform | Build and test member signup and KYC (identity verification) flow | High | CEO/CTO | Complete |  | 2026-05-07 |  | Use Stripe Identity, Persona, or equivalent ¦ Stripe Identity wired at src/app/api/kyc/{start,status,webhook}/. Onboarding flow at /onboarding (handoff to /account/verification per audit fix queued) | All
84 | Technology & Platform | Build and test rental booking flow: calendar, pricing, deposit collection, confirmation | High | CEO/CTO | In Progress |  |  |  | Rental flow shipped at src/app/rent/[symbol]; uses static dates currently. Calendar wiring pending (business audit T2.8) | All
85 | Technology & Platform | Build and test co-ownership marketplace: vehicle listings, share availability, application form | High | CEO/CTO | Complete |  | 2026-05-07 |  | Marketplace at src/app/markets/, full /markets/[symbol] anatomy: provenance + originality + ops disclosure + classic.com live widget + curated comparables | All
86 | Technology & Platform | Build and test co-owner dashboard: booking calendar, usage logs, cost reports, share value | High | CEO/CTO | Complete |  | 2026-05-07 |  | Member dashboard at src/app/{account,my-cars,portfolio,inside}/, sample-data demo banner gated by NEXT_PUBLIC_DEMO_MODE | All
87 | Technology & Platform | Integrate payment processing (Stripe or equivalent) — bookings, deposits, fees | High | CEO/CTO | Complete |  | 2026-05-07 |  | Stripe Checkout + idempotent webhooks: src/app/api/share-purchase/{create-checkout,webhook,intent}/ | All
88 | Technology & Platform | Build and test automated emails: confirmations, reminders, post-rental follow-up | High | CEO/CTO | In Progress |  |  |  | Resend wired for: auth magic link, share-purchase fulfillment + LLC amendment PDF, ops alerts (notifyTeam). Missing per audit: booking confirmation, KYC failed, ACH bounced | All
89 | Technology & Platform | Build admin dashboard: members, listings, bookings, payments, partner commissions | High | CEO/CTO | Complete |  | 2026-05-07 |  | Admin tools at src/app/admin/{,llc,comparables,vehicle-enrichment,audit}/, all admin-role-gated | All
90 | Technology & Platform | Build vehicle inspection photo upload flow for pre/post handover documentation | High | CEO/CTO | In Progress |  |  |  | PhotoGallery component supports multi-photo + lightbox. Upload flow for handover photos pending (admin-side) | All
91 | Technology & Platform | Install and test GPS / telematics tracking in all co-ownership vehicles | High | CEO/CTO + CFO/COO | Not Started |  |  |  | NOT STARTED. Mentioned in /trust-and-safety as future. Will need real fleet first | All
92 | Technology & Platform | Set up email marketing platform (Klaviyo, Mailchimp) with welcome and nurture flows | High | CEO/CTO + CRO/CSO | In Progress |  |  |  | Resend transactional wired. No Klaviyo/Mailchimp marketing nurture flow yet | All
93 | Technology & Platform | Install analytics: Google Analytics, Search Console, Meta Pixel, TikTok Pixel | High | CEO/CTO | Complete |  | 2026-05-07 |  | Required for paid advertising performance tracking ¦ PostHog (posthog-js + posthog-node) + Vercel Analytics + Vercel Speed Insights candidate + Google Search Console (verified) + Bing Webmaster Tools (verified) + Sentry | All
94 | Technology & Platform | Conduct platform security review and penetration test before launch | High | CEO/CTO | Not Started |  |  |  |  | All
95 | Technology & Platform | Establish data backup and disaster recovery process | High | CEO/CTO | Not Started |  |  |  |  | All
96 | Technology & Platform | Set up customer support ticketing system (Intercom, Zendesk, or equivalent) | Medium | CEO/CTO | Not Started |  |  |  | NOT STARTED. /contact form + Resend currently. Intercom/Zendesk pending | All
97 | Technology & Platform | Register all social media handles (@ryda across Instagram, TikTok, YouTube, Facebook) | High | CEO/CTO + CRO/CSO | Not Started |  |  |  |  | All
98 | Technology & Platform | Build and publish market-specific landing pages for each launch city | High | CEO/CTO | Complete |  | 2026-05-07 |  | src/app/locations/{,miami,los-angeles,new-york}/page.tsx — index page added in commit e104572 | All
99 | Technology & Platform | Set up business email addresses for all founders (firstname@ryda.com) | Medium | CEO/CTO | In Progress |  |  |  | Cloudflare Email Routing forwards support@ryda.pro to ops Gmail. No Workspace/Fastmail mailboxes yet (see docs/email-aliases.md) | All
100 | Technology & Platform | Maintain software license inventory — all SaaS tools, licenses, and renewal dates | Medium | CEO/CTO | Not Started |  |  |  | Adapt from M&A DD: track all software in use | All
101 | Technology & Platform | Establish platform uptime monitoring and alerting (PagerDuty, Datadog, or equivalent) | Medium | CEO/CTO | In Progress |  |  |  | Sentry installed. No PagerDuty/Datadog uptime monitoring yet | All
DATA PRIVACY & SECURITY
102 | Data Privacy & Security | Determine which privacy laws apply: CCPA (CA), FL privacy law, federal | High | Legal + CEO/CTO | In Progress |  |  |  | CCPA applies when serving CA members ¦ Partial: CCPA + FL covered in /legal/privacy. GDPR section + named processors pending (audit T3.1) | All
103 | Data Privacy & Security | Designate a privacy officer or assign privacy responsibility to a founder | High | CEO/CTO | Not Started |  |  |  | Can be informal at early stage — must be documented | All
104 | Data Privacy & Security | Document all categories of personal information collected from members | High | CEO/CTO + Legal | Not Started |  |  |  | Name, email, phone, ID, payment, KYC data, usage logs | All
105 | Data Privacy & Security | Draft and publish member-facing privacy policy on ryda.com | High | Legal | In Progress |  |  |  | Must disclose data collection, use, sharing, retention ¦ Drafts at /legal/{privacy,terms,cookies,accessibility,disclaimer}. Audit flagged needs expansion | All
106 | Data Privacy & Security | Establish data retention and deletion policy — how long is member data kept? | High | CEO/CTO + Legal | Not Started |  |  |  |  | All
107 | Data Privacy & Security | Implement data encryption — at rest and in transit for all member PII | High | CEO/CTO | Complete |  | 2026-05-07 |  | TLS for transit; AES-256 or equivalent at rest ¦ TLS via Vercel/Cloudflare. Supabase storage encrypted at rest. Stripe tokenization (no raw card data). PII encrypted in Supabase columns where applicable | All
108 | Data Privacy & Security | Implement access controls — who on the team can access member data? | High | CEO/CTO | Complete |  | 2026-05-07 |  | Role-based access; principle of least privilege ¦ Role-based via auth.users.app_metadata.role === "admin" (service-role-only writable). See src/lib/admin-auth.ts. Tested and gates all /admin/* + /api/admin/* routes | All
109 | Data Privacy & Security | Conduct vendor data security review for all third-party tools handling PII | High | CEO/CTO | Not Started |  |  |  | Stripe, KYC provider, email platform, CRM | All
110 | Data Privacy & Security | Establish data breach response plan — notification timelines, responsibilities | High | CEO/CTO + Legal | Not Started |  |  |  | FL requires notification within 30 days of discovery | All
111 | Data Privacy & Security | Train all team members on data handling and privacy obligations | Medium | CEO/CTO | Not Started |  |  |  | Annual training recommended | All
112 | Data Privacy & Security | Confirm payment card data handling is PCI-DSS compliant via Stripe or equivalent | High | CEO/CTO | Complete |  | 2026-05-07 |  | Never store raw card data — use tokenization ¦ All payments via Stripe Checkout; PCI-DSS Level 1 compliance inherited. No raw card data ever touches RYDA. See src/app/api/share-purchase/create-checkout/ | All
113 | Data Privacy & Security | Establish process for member data deletion requests (CCPA right to delete) | Medium | CEO/CTO + Legal | Not Started |  |  |  | Required for CA members; good practice for all | All
114 | Data Privacy & Security | Implement two-factor authentication for all internal admin systems | High | CEO/CTO | Not Started |  |  |  |  | All
115 | Data Privacy & Security | Conduct annual security audit or penetration test | Medium | CEO/CTO | Not Started |  |  |  |  | All
HR & PEOPLE
116 | HR & People | Document founder roles, responsibilities, and time commitment expectations | High | CEO/CTO | Not Started |  |  |  | Prevent misalignment early | All
117 | HR & People | Establish contractor vs. employee classification policy — get it right from day one | High | Legal + CFO/COO | Not Started |  |  |  | Misclassification is a significant legal risk | All
118 | HR & People | Draft offer letter / contractor agreement template for all new hires | High | Legal | Not Started |  |  |  | Include IP assignment, confidentiality, non-solicit | All
119 | HR & People | Set up background check process for all team members and contractors | High | CFO/COO | Not Started |  |  |  | Especially important given access to member data and HNW clients | All
120 | HR & People | Establish onboarding checklist for new team members and contractors | Medium | CFO/COO | Not Started |  |  |  | Platform access, tools, NDA, handbook, role overview | All
121 | HR & People | Draft employee handbook when first W-2 employee is hired | Medium | Legal + CFO/COO | Not Started |  |  |  | Required in most states; covers policies, conduct, PTO | All
122 | HR & People | Establish PTO and leave policies | Medium | CFO/COO | Not Started |  |  |  |  | All
123 | HR & People | Set up payroll once first W-2 employee is hired (Gusto, Rippling, ADP) | High | CFO/COO | N/A |  | 2026-05-07 |  | Future: payroll setup deferred until first W-2 hire | All
124 | HR & People | Obtain workers' compensation insurance when first employee is hired (FL required) | High | CFO/COO | N/A |  | 2026-05-07 |  | FL requires workers' comp for most employers with 4+ employees; get ahead of it ¦ Future: workers comp triggers at 4+ FL employees | All
125 | HR & People | Establish anti-harassment and equal employment opportunity policy | Medium | Legal + CFO/COO | Not Started |  |  |  |  | All
126 | HR & People | Set up performance review cadence for team | Low | CEO/CTO | Not Started |  |  |  | Annual minimum; quarterly recommended for early team | All
127 | HR & People | Establish compensation benchmarking — ensure team pay is competitive | Medium | CEO/CTO + CFO/COO | Not Started |  |  |  |  | All
128 | HR & People | Document driver vetting process — all people who will drive RYDA or co-owner vehicles | High | CFO/COO | Not Started |  |  |  | MVR check, license verification, insurance authorization | All
129 | HR & People | Conduct background and MVR checks on all staff who handle vehicle handovers | High | CFO/COO | Not Started |  |  |  |  | All
130 | HR & People | Confirm work authorization (I-9) compliance for any employees hired | High | CFO/COO | Not Started |  |  |  |  | All
OPERATIONS — RENTAL
131 | Operations — Rental | Research and rank all exotic / luxury rental operators in Miami (target 8–15) | High | CFO/COO | Not Started |  |  |  | Prioritize operators with strong fleet quality and professionalism | All
132 | Operations — Rental | Outreach to top 5 Miami rental operators — present RYDA partnership value proposition | High | CEO/CTO + CRO/CSO | Not Started |  |  |  | Commission-only model; zero cost to partner | All
133 | Operations — Rental | Sign listing agreements with minimum 2 Miami rental operators before launch | High | CEO/CTO + Legal | Not Started |  |  |  |  | All
134 | Operations — Rental | Review each partner's insurance certificates — confirm vehicles are fully covered | High | CFO/COO | Not Started |  |  |  | RYDA must not hold any insurance liability on rental vehicles | All
135 | Operations — Rental | Review each partner's handover process — confirm it meets RYDA quality standards | High | CFO/COO | Not Started |  |  |  | Inspect facility, meet staff, do a test handover | All
136 | Operations — Rental | Confirm pricing, availability, and blackout dates with each partner | High | CFO/COO | Not Started |  |  |  |  | All
137 | Operations — Rental | Arrange professional RYDA-branded photo session for each listed vehicle | High | CRO/CSO + CFO/COO | Not Started |  |  |  |  | All
138 | Operations — Rental | Create vehicle listings on RYDA platform: photos, specs, pricing, availability | High | CEO/CTO | Not Started |  |  |  |  | All
139 | Operations — Rental | Test complete booking flow end-to-end for each listed vehicle | High | CEO/CTO | Not Started |  |  |  | From search → booking → payment → confirmation → partner alert | All
140 | Operations — Rental | Confirm commission payment routing — how and when RYDA pays partners | High | CFO/COO + CEO/CTO | Not Started |  |  |  |  | All
141 | Operations — Rental | Publish rental FAQ, policies, and member waiver on ryda.com | High | CEO/CTO + Legal | Not Started |  |  |  |  | All
142 | Operations — Rental | Establish post-rental follow-up sequence — automated email + personal outreach | High | CEO/CTO + CRO/CSO | Not Started |  |  |  | Conversion to co-ownership inquiry goal: 30%+ | All
143 | Operations — Rental | Establish rental dispute resolution process — damage claims, late returns, cancellations | High | CFO/COO + Legal | Not Started |  |  |  |  | All
144 | Operations — Rental | Build quality control checklist for evaluating new rental partner applications | Medium | CFO/COO | Not Started |  |  |  |  | All
145 | Operations — Rental | Replicate Miami rental partner process for LA launch (Year 2) | High | CFO/COO | Not Started |  |  |  |  | Year
146 | Operations — Rental | Replicate Miami rental partner process for NYC launch (Year 3) | High | CFO/COO | Not Started |  |  |  |  | Year
OPERATIONS — CO-OWNERSHIP
147 | Operations — Co-Ownership | Identify and secure premium auto storage facility in Miami (climate-controlled, 24/7 access) | High | CFO/COO | Not Started |  |  |  |  | All
148 | Operations — Co-Ownership | Sign storage partnership agreement — Miami | High | CFO/COO + Legal | Not Started |  |  |  |  | All
149 | Operations — Co-Ownership | Identify and contract detailing partner in Miami — SLA, turnaround, pricing | High | CFO/COO | Not Started |  |  |  | Pre/post handover detail required every time | All
150 | Operations — Co-Ownership | Confirm roadside assistance coverage for all co-ownership vehicles in Miami | High | CFO/COO | Not Started |  |  |  |  | All
151 | Operations — Co-Ownership | Build vehicle sourcing pipeline — Channel 1: rental partner fleet rotations | High | CEO/CTO + CFO/COO | Not Started |  |  |  | Ask partners about aging or underperforming fleet | All
152 | Operations — Co-Ownership | Build vehicle sourcing pipeline — Channel 2: independent owner outreach via social media | High | CRO/CSO + CEO/CTO | Not Started |  |  |  | Post social: 'Rarely drive your exotic? RYDA can help' | All
153 | Operations — Co-Ownership | Build vehicle sourcing pipeline — Channel 3: CPO dealer relationships (Porsche, Ferrari, Lamborghini) | High | CFO/COO + CEO/CTO | Not Started |  |  |  | Position RYDA as recurring buyer of 60+ day inventory | All
154 | Operations — Co-Ownership | Establish independent vehicle appraisal process — approved mechanic per market | High | CFO/COO | Not Started |  |  |  | Required for every vehicle before purchase | All
155 | Operations — Co-Ownership | Establish vehicle history report requirement (Carfax or equivalent) for every sourced vehicle | High | CFO/COO | Not Started |  |  |  |  | All
156 | Operations — Co-Ownership | Build co-owner application and qualification process — financial verification, KYC | High | CEO/CTO + CFO/COO | Not Started |  |  |  |  | All
157 | Operations — Co-Ownership | Establish minimum co-owner group size policy (minimum 3, target 5–6) | High | CEO/CTO | Not Started |  |  |  |  | All
158 | Operations — Co-Ownership | Build vehicle LLC formation process — step-by-step from group commit to vehicle purchase | High | Legal + CFO/COO | Complete |  | 2026-05-07 |  | Provider-agnostic adapter at src/lib/llc-formation/ + Firstbase client + mock mode. Admin UI at /admin/llc/{,new,[id]}/. Migration 0022 for llc_entities + llc_formation_events tables | All
159 | Operations — Co-Ownership | Form first vehicle LLC (RYDA Porsche 911 Miami LLC or equivalent) | High | Legal | Not Started |  |  |  |  | All
160 | Operations — Co-Ownership | Collect co-owner funds into vehicle LLC bank account before vehicle purchase | High | CFO/COO | Not Started |  |  |  |  | All
161 | Operations — Co-Ownership | Purchase first co-ownership vehicle — title in vehicle LLC name | High | CFO/COO + Legal | Not Started |  |  |  |  | All
162 | Operations — Co-Ownership | Insure first co-ownership vehicle — all co-owners as named insureds | High | CFO/COO | Not Started |  |  |  |  | All
163 | Operations — Co-Ownership | Complete 360-degree pre-delivery inspection and photo documentation | High | CFO/COO | Not Started |  |  |  | Uploaded to platform; shared with all co-owners | All
164 | Operations — Co-Ownership | Document and train on vehicle handover protocol — pre/post inspection, fuel, keys | High | CFO/COO | Not Started |  |  |  |  | All
165 | Operations — Co-Ownership | Open booking calendar for first co-owner group | High | CEO/CTO | Not Started |  |  |  |  | All
166 | Operations — Co-Ownership | Send welcome package to co-owner group — platform guide, protocol, contacts, emergency numbers | High | CFO/COO + CRO/CSO | Not Started |  |  |  |  | All
167 | Operations — Co-Ownership | Establish annual vehicle valuation update process — revalue each vehicle annually | Medium | CFO/COO + CPA | Not Started |  |  |  | Drives management fee and share transfer pricing | All
168 | Operations — Co-Ownership | Establish maintenance reserve fund collection and management per vehicle LLC | High | CFO/COO | Not Started |  |  |  | Typically $150–$300/co-owner/month into reserve | All
169 | Operations — Co-Ownership | Build share transfer / exit process — listing, verification, legal transfer, commission | High | CEO/CTO + Legal | In Progress |  |  |  | Process documented at /how-it-works#exit. UI at /admin/comparables/[symbol] for valuation comps. Formal legal protocol pending counsel | All
170 | Operations — Co-Ownership | Establish vehicle condition standard for transfers — inspection required before any share sale | High | CFO/COO | Not Started |  |  |  |  | All
171 | Operations — Co-Ownership | Replicate Miami co-ownership operations for LA launch (Year 2) | High | CFO/COO | Not Started |  |  |  | Storage, detailing, mechanic, handover protocol | Year
172 | Operations — Co-Ownership | Replicate Miami co-ownership operations for NYC launch (Year 3) | High | CFO/COO | Not Started |  |  |  | NJ storage facility; NYC delivery capability | Year
MARKETING & GTM
173 | Marketing & GTM | Define brand identity — logo, color palette, tone of voice, visual guidelines | High | CEO/CTO + CRO/CSO | Complete |  | 2026-05-07 |  | Foundation for all marketing materials and messaging ¦ See task 80 | All
174 | Marketing & GTM | Build and launch ryda.com — brand story, services overview, waitlist signup | High | CEO/CTO | Complete |  | 2026-05-07 |  | Primary digital storefront — must be live before any paid campaigns ¦ ryda.pro live with auto-deploy from main; SEO infra (JSON-LD, sitemap, robots.txt, OG images, GSC, Bing) all wired | All
175 | Marketing & GTM | Set up waitlist landing page — capture name, email, city, interest, vehicle preference | High | CEO/CTO | Complete |  | 2026-05-07 |  | Waitlist API at src/app/api/waitlist/route.ts; captures email + market + interest. Signup flow at /signup | All
176 | Marketing & GTM | Build email welcome and nurture sequence for waitlist signups | High | CEO/CTO + CRO/CSO | In Progress |  |  |  | Automate lead nurturing from day one ¦ Auth magic-link flow wired. Marketing nurture (multi-touch) pending Klaviyo/Mailchimp setup | All
177 | Marketing & GTM | Launch social media accounts — Instagram, TikTok, YouTube, Facebook | High | CRO/CSO + CEO/CTO | Not Started |  |  |  | Consistency over production value early on ¦ NOT STARTED. Playbook ready at docs/social-launch-playbook.md. User-side: claim handles + upload profile pic | All
178 | Marketing & GTM | Create 90-day content calendar — 5+ posts/week across primary channels | High | CRO/CSO | Not Started |  |  |  | Pillars: real cost of ownership, behind the scenes, supercar content | All
179 | Marketing & GTM | Set up paid ads infrastructure — Meta Business Manager, TikTok Ads, pixels, custom audiences | High | CEO/CTO + CRO/CSO | Not Started |  |  |  |  | All
180 | Marketing & GTM | Launch paid acquisition campaign targeting HNW audiences for waitlist signups | High | CRO/CSO + CEO/CTO | Not Started |  |  |  |  | All
181 | Marketing & GTM | Reach 150+ qualified waitlist signups in launch market before first vehicle goes live | High | CRO/CSO + CEO/CTO | Not Started |  |  |  | Key milestone to validate demand before vehicle acquisition | All
182 | Marketing & GTM | Develop referral partner program — structure, commission rates, tracking, onboarding materials | High | CRO/CSO + CEO/CTO | Not Started |  |  |  | Scalable channel for ongoing member acquisition | All
183 | Marketing & GTM | Identify and sign luxury real estate agent referral partners in launch market | High | CRO/CSO | Not Started |  |  |  | Referral fee per completed co-owner signup | All
184 | Marketing & GTM | Identify and sign private wealth advisor and family office referral partners | Medium | CRO/CSO | Not Started |  |  |  |  | All
185 | Marketing & GTM | Establish hotel concierge and hospitality venue referral relationships | Medium | CRO/CSO | Not Started |  |  |  | Drive rental bookings and top-of-funnel awareness | All
186 | Marketing & GTM | Identify yacht broker and private aviation referral partners | Medium | CRO/CSO | Not Started |  |  |  |  | All
187 | Marketing & GTM | Build PR target list — luxury lifestyle, automotive, and business media outlets | High | CRO/CSO + CEO/CTO | Not Started |  |  |  | Earned media is highest-trust channel for HNW audience | All
188 | Marketing & GTM | Pitch launch story to top-tier press — Forbes, Robb Report, Bloomberg, local luxury media | High | CEO/CTO + CRO/CSO | Not Started |  |  |  |  | All
189 | Marketing & GTM | Plan and execute a launch event — fleet display, member networking, press invite | High | CRO/CSO + CEO/CTO | Not Started |  |  |  | High-impact event for press, partners, and prospect conversion | All
190 | Marketing & GTM | Build first co-owner group via personal outreach — founder-led closing of initial members | High | CEO/CTO + CRO/CSO | Not Started |  |  |  |  | All
191 | Marketing & GTM | Launch member community channel — private WhatsApp or Slack group for co-owners | Medium | CRO/CSO | Not Started |  |  |  | Retention + community building from first cohort | All
192 | Marketing & GTM | Establish bi-weekly member email newsletter — new vehicles, updates, member stories | Medium | CRO/CSO | Not Started |  |  |  |  | All
193 | Marketing & GTM | Plan first member experience event — track day, rally, or exclusive gathering | Medium | CRO/CSO | Not Started |  |  |  | Retention + acquisition event | All
194 | Marketing & GTM | Set up referral partner payment process — track referrals, verify completions, pay fees | High | CFO/COO | Not Started |  |  |  | Track referrals, verify completions, pay fees | All
195 | Marketing & GTM | Build playbook to replicate marketing and outreach for expansion into new markets | Medium | CRO/CSO + CEO/CTO | Not Started |  |  |  | Repeatable GTM template for each new city | All
ONGOING COMPLIANCE
196 | Ongoing Compliance | Annual LLC renewals — RYDA LLC and all vehicle LLCs in all operating states | High | CFO/COO + Legal | Not Started |  |  |  |  | All
197 | Ongoing Compliance | Annual federal and state tax returns for RYDA LLC and all vehicle LLCs | High | CFO/COO + CPA | Not Started |  |  |  |  | All
198 | Ongoing Compliance | Annual K-1 issuance to all co-owners for each vehicle LLC | High | CFO/COO + CPA | Not Started |  |  |  |  | All
199 | Ongoing Compliance | Annual 1099 issuance to all qualifying contractors and referral partners | High | CFO/COO | Not Started |  |  |  |  | All
200 | Ongoing Compliance | Annual insurance policy renewals — fleet, GL, D&O, E&O, cyber | High | CFO/COO | Not Started |  |  |  |  | All
201 | Ongoing Compliance | Annual vehicle valuations — update management fees and share transfer pricing | High | CFO/COO + CPA | Not Started |  |  |  |  | All
202 | Ongoing Compliance | Annual review of all legal templates — co-owner agreement, listing agreement, waiver | Medium | Legal | Not Started |  |  |  | Laws change; templates should be reviewed annually | All
203 | Ongoing Compliance | Annual data privacy audit — review what data is collected, stored, and shared | Medium | CEO/CTO + Legal | Not Started |  |  |  |  | All
204 | Ongoing Compliance | Annual cybersecurity assessment or penetration test | Medium | CEO/CTO | Not Started |  |  |  |  | All
205 | Ongoing Compliance | Annual review of platform terms of service and privacy policy | Medium | Legal | Not Started |  |  |  |  | All
206 | Ongoing Compliance | Maintain corporate records — meeting minutes, resolutions, amendments for all LLCs | High | Legal + CFO/COO | Not Started |  |  |  |  | All
207 | Ongoing Compliance | Quarterly review of co-owner payment status — management fees, maintenance reserves | High | CFO/COO | Not Started |  |  |  | Identify delinquencies early | All
208 | Ongoing Compliance | Quarterly financial review against budget — by market and revenue stream | High | CFO/COO | Not Started |  |  |  |  | All
209 | Ongoing Compliance | Quarterly review of rental partner performance — bookings, commissions, quality issues | Medium | CFO/COO + CRO/CSO | Not Started |  |  |  |  | All
210 | Ongoing Compliance | Quarterly vehicle condition inspections — all co-ownership vehicles | High | CFO/COO | Not Started |  |  |  | Document condition, log any maintenance needed | All
211 | Ongoing Compliance | Monitor for new state / local regulations affecting vehicle rentals or co-ownership | Medium | Legal | Not Started |  |  |  | Regulatory landscape is evolving for shared vehicle models | All
212 | Ongoing Compliance | FinCEN / AML awareness — monitor for any obligations related to high-value asset transactions | Medium | Legal + CFO/COO | Not Started |  |  |  | Co-ownership of high-value assets may trigger reporting obligations | All

## Summary Dashboard
RYDA ¦ TRACKER SUMMARY DASHBOARD
WORKSTREAM SUMMARY — Task Count by Status
Workstream | Total Tasks | Not Started | In Progress | Complete | N/A | % Complete | Priority: High
Company Formation | 16 | 15 | 0 | 0 | 1 | 0% | 11
Legal & Contracts | 19 | 13 | 5 | 0 | 1 | 0% | 12
Finance & Accounting | 15 | 13 | 1 | 0 | 1 | 0% | 10
Tax & Compliance | 15 | 14 | 0 | 0 | 1 | 0% | 12
Insurance | 13 | 12 | 0 | 0 | 1 | 0% | 7
Technology & Platform | 23 | 6 | 6 | 10 | 1 | 43% | 19
Data Privacy & Security | 14 | 9 | 2 | 3 | 0 | 21% | 11
HR & People | 15 | 13 | 0 | 0 | 2 | 0% | 9
Operations — Rental | 16 | 16 | 0 | 0 | 0 | 0% | 15
Operations — Co-Ownership | 26 | 24 | 1 | 1 | 0 | 4% | 25
Marketing & GTM | 23 | 19 | 1 | 3 | 0 | 13% | 16
Ongoing Compliance | 17 | 17 | 0 | 0 | 0 | 0% | 10
TOTAL | 212 | 171 | 16 | 17 | 8 | 8% | 157